## 2018
Abbot's Mill Project Arrowhead Action Plan 2018-19
Activity | Start date/Timescale | Expected Outcomes | Lead | Partners | Funding | Activity agreed in principle or proposed
Follow-up bird survey (first undertaken 2013) | 2018-07-01 | Bird survey complete | RSPB/KWT | AMP | In kind | Proposed - AMP to follow up with existing KWT/RSPB partners/contacts
Reptile and amphibian survey (first undertaken in 2013) | 2018-07-01 | Reptile and amphibian survey complete | KRAG | AMP | In kind | Agreed in principle
Follow-up small mammal survey, to be repeated at regular intervals to enable longitudinal assessment of improved habitat. (First undertaken in 2012) | 2018-07-01 | Small mammal survey completed providing comparison with previous survey | KMG | AMP | In kind | Agreed in principle
Water quality assessment | 2018-08-01 | Water quality assessment complete | EA | AMP | In kind | Agreed in principle
Follow-up invertebrate survey (first undertaken in 2012) | 2018-08-01 | Invertebrate survey complete | CCCU/DICE | AMP, EA | In kind | Agreed in principle
Fish and aquatic species survey | 2018-08-01 | To provide comparison with previous surveys (2012) | EA | AMP, DICE | In kind | Agreed with EA in principle
All survey work pulled together to ascertain improvements to date to biodiversity as well as priority areas for the coming years. (Phase One Habitat Survey) | 2018-09-01 | Phase One Habitat Survey complete | CCCU | AMP | AMP/CCCU - In kind | Agreed in principle
Fencing around car park and end of arrowhead (in accordance with Riverside Strategy) and locked gate at the front of AMP land to improve security at night. (Native hedging to follow in the autumn according to approved tree-management plan) | 2018-09-01 | More secure site at night and improved public access during the daytime. | AMP | CCC, FoR | AMP/in kind/grant application | AMP to work with FoR and CCC to agree design of fencing in line with Riverside Strategy.
Follow-up bat survey (first undertaken 2012) | 2018-09-01 | Bat surveys completed providing comparison with previous surveys | KBG | AMP | In kind | Agreed in principle
Continue work to create and improve nesting, breeding and feeding habitats (including adding nesting boxes and insect and wildlife houses) for wildlife, other than the river and banks. | 2018-10-01 | Encouraging more wildlife to the site in line with UK Post-2010 Biodiversity Framework | DICE students and AMP volunteers to undertake the leg work | KMG, KBG, Perm, Bio Expert panel partners | In kind | Agreed in principle
Regular Bio-Blitz - biodiversity survey in partnership with CCCU Ecology Group (first carried out in May 2014) | 2018-10-01 | Bio-blitz results recorded and compared with previous surveys. | CCCU | AMP | In kind - AMP/CCCU | Agreed, date tbc
Fungi survey | 2018-10-01 | Survey completed | DICE/AMP | DICE, AMP | In kind | Agreed in principle
Run workshops involving volunteers/local residents/students and schools to work on action plan. To include design and planting plan. All to be based on aims of the UK Post-2010 Biodiversity Framework. | 2018-10-01 | 2 half day workshops. Action plan to be a learning experience - the process is important as the outcome. | AMP to co-ordinate | Perm, Bio Expert Panel | In kind and grants | Agreed in principle. Dates tbc
Tree work for habitat restoration commences; working from tree management plan (see attached). | 2018-11-01 | Tree survey and risk assessment of trees on site undertaken prior to tree work. Long-term plan of felling (minimal), shredding, pollarding and coppicing as necessary to open up the canopy and improve biodiversity of the area. Native-tree hedge added around the arrowhead to provide winter shelter and food for wildlife). | AMP | AMP, Woodwarden, CCCU | Woodwarden (In kind)/CCCU (In kind) | Dependant on CCC approving tree-management plan
Assessment to determine amount of concrete on the site. | 2018-11-01 | Amount, and location of any concrete known | AMP | CCCU, EA | AMP/PL/In kind | AMP to undertake
Assessment to determine amount of asbestos on the site | 2018-11-01 | Amount, and location of any asbestos known | AMP to identify contractor |  | In kind (through contractor)/PL | AMP to undertake
Native species (tree, shrub and wildflower) planting commences on arrowhead; working from management plan | 2018-12-01 | Work started - on-going improvement of the site in line with UK Post-2010 Biodiversity Framework | AMP | AMP, Perm, Bio Expert panel | In kind | Agreed in principle
Remove construction waste (including asbestos if found) dumped on edge of arrowhead/car park. | 2019-01-01 | Site prepared for on-going tree and planting work | AMP to identify contractor |  | AMP to fund/In kind/PL | AMP to undertake
Remove concrete blocks | 2019-01-01 | Site improved for biodiversity enhancment and habitat restoration. | AMP to liaise with EA re. using their digger to help break up and remove concrete | AMP, EA, CCCU | AMP to fund/In kind/PL | Already agreed with EA in principle
Continuation of woodchip path around arrowhead | 2019-01-01 | Improved public access around the site without encroaching on wildlife habitats.
Commence work to improve the river and banks - adding low flow channel, softening banks, coir matting/willow faggots/spiling/planting on banks, creating and improving nesting, breeding and feeding habitats for wildlife, including long-term removal of ivy to help encourage water voles back to the area. | Tbc | River and banks improved for wildlife. | EA | EA, KSCP, AMP, Perm | EA to identify budget. AMP agreed to match fund in kind. | Already agreed with EA in principle

## Abbot's Mill Team
Jo Kidd | Co-founder/Executive Director | Jo has been a keen environmentalist and community activist and organiser for over 30 years. Jo strives to live as sustainably and ethically as possible and is vegan. Jo has a BA (Hons) in Social Anthropology and Politics and Government, an MA in Social Anthropology from the University of Kent at Canterbury and a Postgraduate Certificate in Education (PCET - Post Compulsory Education and Training) from Greenwich University. She co-founded Skillnet Group Community Interest Company in 2001 and was its founding CEO until May 2013. Skillnet Group is a social enterprise that supports people with and without learning disabilities to work together to make differences and build connections within communities. Jo is the founder and lead organiser of the Kent Vegan Festival and is currently setting up a veganic (vegan - organic) farm in alongside her husband, Terry Thompson. Jo is a free-lance consultant in the field of social justice and disability rights, a fellow of the Centre for Welfare Reform and sits on the Editorial Board of the Tizard Learning Disability Review. Jo enjoys walking, travelling, languages and spending time with her family and lives in Boughton-Under-Blean with her husband, Terry Thompson and their daughter, Rosa.
Terry Thompson | Co-founder/Technical Director | Terry is a local entrepreneur and has had an active interest in sustainable living and renewable energy for over 30 years. He is also a community activist and organiser and a vegan. He is qualified in agricultural mechanics and advanced welding and formerly lectured on motor vehicle technology at a local Further Education College. He has developed a sustainable community/business hub in Canterbury (Roper Yard) and also co-founded Skillnet Group, in partnership with his wife, Jo. He runs a sustainable wood enterprise in nearby Chartham Hatch, based on a high level forestry stewardship scheme. The aim of this is to manage and coppice woodland to produce low carbon fuel and sustainable wooden products. He is currently setting up a vegan organic farm alongside his wife, Jo Kidd. Terry is a keen amateur actor and singer in his spare time.
Derek Read | Chair | Derek has a BSc in Engineering with Economics and an MA in Industrial Economics from Sussex University. He has worked in the computing industry for nearly 40 years and is, currently, owner of a technology company, Diam Software Limited that has designed and built a toolset for the rapid development of application software. In addition he is a non executive director, and shareholder, of three other technology firms that have used the technology to develop applications for sale in the finance and language interpretation industries. He has been involved as a trustee/director for a number of charities over the past 15 years, mainly supporting people experiencing mental ill health and/or learning difficulties. He lives in Canterbury with his wife, Pam.
Helen Simpson | Director of Social Justice | Helen is a passionate educator and researcher who has 25 years’ experience of teaching in primary and secondary schools, as well as running children’s clubs, GCSE tutoring and teaching adults in 1:1, small group and commercial language school settings. She completed her MAEd in 2012, with a final dissertation on the use of stories in different languages in Primary Languages. This developed her interest in the role of Language Awareness in Primary Languages, in particular in relationship to social justice. As Director of the Development Education charity, World Education Development Group (WEDG), Helen developed projects that promoted social justice and Global Learning in schools. Helen currently works in a local primary school and on a Global Learning Project Innovation Fund curriculum development project, creating cross-curricular links to promote linguistic equality. Helen enjoys family life, walking, reading and spending time in France, as well as volunteering for and sitting on the boards of the Abbot's Mill Project and Ethnic Minority Independent Council in Canterbury.
Nicola Waddington | Head of Heritage | Nicola Waddington lives in Canterbury and is an archive and heritage consultant. She has an MA in Archives and Records Management and has worked with written heritage and community engagement with heritage for the last 15 years.
Nicholas Thurston | Planning consultant | Nicholas Thurston MA MEng Cantab. Nicholas studied Chemical Engineering, specialising in environmental engineering, and has experience of a wide range of environmental projects for two water companies, a Christian water charity in Chad, and an environmental engineering consultancy in Europe and the US. Nicholas achieved chartered status in 2001 and currently works for the University of Kent as a Projects Executive. Nicholas has been assisting the Abbot's Mill Project on a voluntary basis, with the planning of the renewable energy project elements. Nicholas has lived in the St Dunstan's area of Canterbury with his family since 2000.
Louise Allen | Project Lead (Be the Change Project) | Louise is a passionate advocate for improving communication, understanding and how we relate to the world and others around us. Over the past 10 years, Louise has been involved in developing and co-leading a number of environmental and community focused projects in Manchester and Kent including working with the Development Education Project, Manchester Environmental Education Network, Action for Sustainable Living, Abbey Physic Community Garden and, most recently, Be The Change, Abbot's Mill Project's young activists group. Louise has worked with Skillnet Group for 9 years. Skillnet is a Community Interest Company working alongside adults with learning difficulties to increase equality and inclusion, and ensure that people are seen, heard and have a sense of belonging within their community. Louise has worked in many projects including managing the Pulse, an eco café set up to enhance and provide work experience and social opportunities for the local community and is now Director of Ethics and Communication for the organisation. Louise has been a Samaritans volunteer for 9 years and is currently training as a counsellor. Louise aims to lead a conscious and responsible life and lives in Faversham with her partner, Todd, and their two children, Maya and Erin.
Katie McDaniel | Admin and Funding Assistant
Regular Volunteer Team | We have a pool of around 50 regular volunteers, including local residents, students and families.

## Expert Partners (Bio)
Expert partners/supporters specific to the arrowhead plan
Organisation/Group | Role
Kent Wildlife Trust | Expert advisers - wildlife/conservation/management
Kent Bat Group | Expert advisers - bats, providing regular bat surveys
Kent Mammal Group | Expert advisers - small mammals, providing regular small mammal surveys
Kent Reptile and Amphibian Group | Expert advisers - reptiles and amphibians, providing regular reptile/amphibian surveys
UKC/Durrell Institute of Conservation and Ecology | Providing students for conservation work and biodiversity improvement
CCCU Ecology Group | Co-ordinating, and providing staff and students for, bio blitzes and phase one habitat survey
Friends of the Riverside | Partnership of local community groups and statutory partners with the aim of improving the river and riverside for all.
Canterbury Archaeological Trust | Leading all archaeological excavations, research and reporting and providing a watching brief where necessary
Pure Leapfrog | Environmental organisation providing pro bono expert consultants from a wide range of areas.
Woodwarden | Qualified tree surgeon (pro bono)
Jo Barker, Dynamic Equilibrium | Permaculture expert
RSPB | Expert advisers - birds
Statutory Partners
CCC
KCC
Kentish Stour Countryside Partnership
Environment Agency

## Proposed Tree Management Plan
The ‘arrowhead’ and Abbot’s Mill sites together with the City Council-managed nature reserve of Bus Company Island, lying just outside the line of the city wall, make up the largest wooded area in the centre of Canterbury. This area is hugely important as it forms a great part of the ‘green’ or biological corridor that follows the River Stour through the city.
The arrowhead has been left un-managed for a number of years and has suffered, from a perspective of biodiversity, as it has been taken over largely by two introduced, though now widely naturalised, species, Sycamore Acer pseudoplantus and Buddleia Buddleja davidii.
The Sycamore is native to the hills and uplands of southern and central Europe. It is a fast growing, vigorous tree which sets seed freely to the extent that it has become in many parts an unwelcome, invasive species tending to become the dominant tree in many wooded areas as it out-competes native species.
Sycamores make a fairly unremarkable contribution to the diversity of wildlife in the UK. In their favour they do support a large aphid population which provide a food source for insect eating birds and a supplementary food source for Dormice Glis glis (not recorded in this area). They also act as host plant for host-specific species such as Sycamore Moth Acronicta aceris and the Sycamore Gall mite Aculops aceriola; however, their value to native wildlife is insignificant when compared to that of the native species of, for example, Pedunculate (English) Oak Quercus robur and Hazel Corylus avellana both of which are of huge importance to woodland wildlife and support an immense variety of vertebrates and invertebrates. Where Sycamore becomes the dominant woodland species their effect on native wildlife is detrimental in that it narrows down the species diversity of an area.
Sycamores, although doing well on some heavy soils, are not ideally suited to very damp or water-logged land and are far from an ideal riverside species. This is in evidence on the trees of the site in question as they are largely in poor condition and have many dead branches.
The quality and biodiversity of this important site would be greatly improved by undertaking some management of the area and the following recommendations could be considered:
1) Thinning out the canopy and removal of dead limbs. This would allow more light to reach the wood floor and allow a greater range of plants to take hold. The Willow Warbler Phylloscopus trochilus which has undergone a serious decline in the UK over the past twenty years used to breed in this area but has been lost as a breeding species, largely due to the unsuitability of the habitat which has become too dense for this low-level nester which prefers a more open environment. Chiffchaff Phylloscopus collybita and Blackcap Sylvia atricalpilla both still breed in the area and it seems that with a little work that Willow Warblers could be encouraged to nest here again.
2) A riparian site such as this would also benefit from the very gradual removal of some of the Sycamores and replacing them with a more suitable native tree. The obvious candidate for this would be Common Alder Alnus glutinosa as this species would bring numerous advantages to the area.
The Alder is a tree quite at home in wet situations where their tough roots are important in stabilising river banks and preventing erosion. This, in turn, would allow most of the Ivy Hedera helix to be removed from the banks. The presence of Ivy on river banks has been shown to discourage their colonisation by Water Voles Arvicola terrestris. The banks of the river here could be made into an ideal habitat for this now very scarce mammal and helping the re-colonisation of the area should be made a priority. The last Water Vole colony in the area vanished about twelve years ago, probably as the result of predation by American Mink Mustela vison. Thankfully there have been no recent sightings of this alien predator in the area for the last ten years and the river banks could again hold Water Vole colonies. (To this end, it would be worth planting Yellow Iris Iris pseudocorus as this is an important food source for the voles).
The leaves of Alder are a food plant for many insects and their cones provide a winter food source for some of our scarcer finches such as Lesser Redpoll Carduelis cabaret and Siskin Carduelis spinus. The replacement of some of the Sycamores with Alder would improve the quality of the above mentioned green corridor through the city and would greatly aid in the movement of fauna through this largely urban area.
3) The bridge on St. Radigund’s Street is being damaged by both Sycamore and Buddleia. The Sycamores growing next to the bridge at the entrance to the Abbot’s Mill site should be removed before their roots begin seriously to undermine the bridge foundations (completed under previous CCC-approved tree management plan).
The bridge itself now holds several large Buddleia bushes and these should be removed immediately before they cause serious damage to the brickwork. This has been reported to KCC several times but remains undone.
4) Some of the land area should be cleared of Buddleia and Bramble Rubus ‘fruticosus’ and a programme of replanting with suitable native species should be undertaken (this work has begun on AMP land and we would like to extend this to the Arrowhead). The area would benefit from the introduction of species such as Hawthorn Crataegus monogyna, Hazel, as mentioned above, which could be coppiced every few years and perhaps also of Yew Taxus baccata which is tolerant both of urban areas and also of shade making it a good under-storey plant. All of these trees would provide valuable winter food and shelter for a number of faunal species.
5) Planting a native-tree hedge around the arrowhead (similar to that around the AMP site) would provide winter food and shelter for many bird, and other faunal species.

## Key and Expert Adviser Panels
Key
AMP - Abbot's Mill Project
EA - Environment Agency
KMG - Kent Mammal Group
KBG - Kent Bat Group
KSCP - Kentish Stour Countryside Partnership
DICE - Durrell Institute of Conservation and Ecology
Perm - Permaculturist
CCCU - Canterbury Christ Church University
RSBP - Royal Society for the Protection of Birds
PL - Pure Leapfrog
CAT - Canterbury Archaeological Trust
CCC - Canterbury City Council
HE - Historic England
KCC - Kent County Council
KWT - Kent Wildlife Trust
KRAG - Kent Reptile and Amphibian Group
FoR - Friends of Riverside
Bio Expert Panel for Arrowhead includes:
AMP, EA, KMG, KBG, KSCP, KRAG, Perm, PL, DICE, CCCU, RSBP, CCC.
Hydro Expert Panel includes:
AMP, EA, CCC, Hydromatch Consulting (micro-hydro specialists), Herrington Consulting, HE.
History/Archaeology Expert Panel includes:
AMP, CAT, CCC, UKC, CCCU, HE, KCC.

## Partners
Key Partners, Funders and Corporate Supporters
Canterbury Archaeological Trust
Canterbury Business Improvement District
Canterbury Christ Church University
Canterbury City Council
Conker Conservation
Crab and Winkle Line Trust
Cripps Harries Hall Solicitors
DICE (Durrell Institute of Conservation and Ecology)
Dynamic Equilibrium
Environment Agency
Friends of the Riverside
Herrington Consulting
Historic England
Hydromatch Consulting (micro-hydro specialists),
Impact PR and Design
Kent Bat Group
Kent County Council
Kent Mammal Group
Kent Reptile and Amphibian Group
Kent Wildlife Trust
Kentish Stour Countryside Partnership
Moorespace Architects
Pure Leapfrog
Pure Magick
Refectory Kitchen
Renewables for Schools
RSPB (Royal Society for the Protection of Birds)
Skillnet Group CIC
Whitefriars
Woodwarden
Grant funders to date:
Brook Trust Fund
Canterbury Area Member Panel Opportunities Fund
Conservation Foundation (Tools Shed),
Greggs Foundation
KCC Members' Fund
Kent Community Foundation